Empire City MC Committee

Folsom Street East Event

Conference Call on Thursday, April 26, 2012 @ 9:00 p.m.

Meeting Minutes

- Committee Members:  Ed Caraballo, Alexander Hadel, Joe Mitchell, Eddie Murphy & Chaz Antonelli

- Attendees:  Ed Caraballo, Chaz Antonelli, Alexander Hadel, Joe Mitchell and Eddie Murphy

- Summary:  Work with ECMC committee members to finalize the below task at hand for the Folsom Street East (FSE) event

- Task at hand:

    - Creating and ordering new club business cards – (Ed Caraballo) – The business cards for FSE have been created and received.  I will share with everyone during our club meeting Wednesday, May 2, 2012.

    - Create ECMC pamphlet to be distributed at the event – (Chaz Antonelli)  - created the initial rough draft copy of the 3 fold pamphlet.  The initial pamphlet was sent out to the FSE committee on Wednesday, April 25, 2012 for review.   The pamphlet will continue to be a work in progress and should be completed prior to our club meeting on Wednesday, May 2, 2012.

    - Give away item – (Joe Mitchell) – is working with Vendo Direct on options for give-a-way items.  So far, he’s received a quote for Pens, Key Rings and Bottle Openers.  Of the 3 choices, the pens were by far the least expensive.  Alexander H. was going to look into other possible vendor options.  We need to finalize our options during today’s call.

- Chaz - Foam Ear plugs

- Joe M. – 250 Black Bottle Cap Opener with Gold or Yellow lettering / logo

    - Volunteers for the event – Ed Caraballo, Will Cordero, Joe Mitchell, Chaz Antonelli, Alexander Hadel (will confirm availability), more volunteers are needed to help manage the people, table and bikes.  More volunteers from club participants is encouraged and will be appreciated.

    - Bikes for the event – we have limited space to accommodate a total of 3 bikes, the skyline banner, 2 chairs, table and tent.  As stated during last week’s FSE committee, if you volunteer to show your motorcycle during the FSE event, you must be in attendance (at our booth) for the full event.

REMINDER:  Prior to volunteering your motorcycle for the event, you must be aware there is always the risk your motorcycle may get scuffed, scratched, dinged or some other type of damage as a result of having people sit on or stand next to your motorcycle.  Empire City MC and Folsom Street East will NOT assume any responsibility for possible damages to your motorcycle

    - Creation of waiver forms to be signed by anyone wanting to take their picture on one of the motorcycle – (Ed Caraballo / Chaz Antonelli) – Ed sent an email to the Folsom Street East coordinators regarding the concern of liability and waiver’s for event participants to sign.  We are currently awaiting the response from FSE.

    - Club logo for the city skyline banner – (Chaz Antonelli) – Work in progress

    - Raffle item / table items – so far we possibly have the following items to Raffle Off:

- Leather Cap  (Possible item from the Leatherman)

- Leather Vest (Possible item from the Leatherman)

- Leather Harness (Eddie M.)

- Chain Harness (Alexander H.)

- Leather Shorts (Chaz A.)

- Individual responsibilities for FSE Event Task:

- Volunteers – Eddie M., Chaz A., Joe M., Alexander H. (possible), Ed C. and Will C.  We can still use a few more volunteers from our club members or friends of ECMC.

- Business Cards – Ed C.

- Raffle Items – Eddie M., Alexander H., Chaz A. & Ed C.

- City Skyline Back Drop  & Logo – Chaz A.

- Tripod for Camera – Ed C.

- Tent for FSE Event – Ed C.

- Possible ice chest with water – Ed C.

- Camera – Eddie M. & Joe M.

- Prototype – Ear Plug Give-A-Way with ECMC logo

- Club Pamphlet – Chaz A.

- Follow up with FSE regarding waiver situation – Ed C.

- As an ongoing project:  Possibly orchestrate reach out opportunity to major motorcycle dealership (i.e. BMW Manhattan, Harley Davidson, Yamaha……etc) to see if we can create a relationship with them and promote Empire City MC

I would like to thank each of you for your contribution in preparing to make the Folsom Street East event a success for Empire City MC